## TEST_PLAN_3
Project group: | Group 8 |  |  |  | Tests made by: | John
[5 empty] | Date: | 2024-04-23
Tests executed by:
Date:
[12 empty] | To do | Hoog
Test case ID | User Story | Acceptance Criteria | Test Design Technique | Test Type | Test Steps | Test data (if applicable) | Expected result | Actual result | Status | Notes | Finding ID | In progress | Gemiddeld
TEST_1 | 1 | 4 | syntactic | System | 1. the user clicks the "log in" button 1. the user clicks the "log in" button |  | The user will be redirected to the following screen to enter a username and password |  |  |  |  | Passed | Laag
[5 empty] | 2. The user enters a valid username and password | Username: EliseBijl Password: Test1234! | The user name and password can be entered in the appropriate fields |  |  |  |  | Failed
[5 empty] | 3. The user clicks the "log in" button |  | The user is successfully logged in and is redirected to the following screen |  |  |  |  | Reopen
TEST_2 | 1 | 5 | decision table | Unit | Unit_test Name_1 | None | PASS
TEST_3 | 1 | 3 | edge | Unit | Unit_test Name_10 | None | PASS
TEST_4 | 2 | 1 | syntactic | System | 1. the user clicks the "log in" button 1. the user clicks the "log in" button |  | The user will be redirected to the following screen to enter a username and password
[5 empty] | 2. The user enters a valid username and password | Username: EliseBijl Password: Test1234! | The user name and password can be entered in the appropriate fields
[5 empty] | 3. The user clicks the "log in" button |  | The user is successfully logged in and is redirected to the following screen
TEST_5 | 1 | 5 | decision table | Unit | Unit_test Name_2 | None | PASS
TEST_6 | 1 | 3 | edge | Unit | Unit_test Name_6 | None | PASS

## Sprint_3
Project group: | Group 8 |  |  |  | Tests made by: | John
[5 empty] | Date: | 2024-04-23
[5 empty] | Tests executed by: | Dennis
[5 empty] | Date: | 30th April
[12 empty] | To do | Hoog
Test case ID | User Story | Acceptance Criteria | Test Design Technique | Test Type | Test Steps | Test data (if applicable) | Expected result | Actual result | Status | Notes | Finding ID | In progress | Gemiddeld
TEST_1 | 1 | 4 | syntactic | System | 1. the user clicks the "log in" button 1. the user clicks the "log in" button |  | The user will be redirected to the following screen to enter a username and password |  | Passed |  |  | Passed | Laag
[5 empty] | 2. The user enters a valid username and password | Username: EliseBijl Password: Test1234! | The user name and password can be entered in the appropriate fields | The user can enter a username, but not a password. | Failed | The password field was missing from the login screen. | FINDING_1 | Failed
[5 empty] | 3. The user clicks the "log in" button |  | The user is successfully logged in and is redirected to the following screen |  | To do |  |  | Reopen
TEST_2 | 1 | 5 | decision table | Unit | Unit_test Name_1 | None | PASS | PASS | Passed
TEST_3 | 1 | 3 | edge | Unit | Unit_test Name_10 | None | PASS | FAIL | Failed |  | FINDING_3
TEST_4 | 2 | 1 | syntactic | System | 1. the user clicks the "log in" button 1. the user clicks the "log in" button |  | The user will be redirected to the following screen to enter a username and password |  | Passed
[5 empty] | 2. The user enters a valid username and password | Username: EliseBijl Password: Test1234! | The user name and password can be entered in the appropriate fields | The user can enter a username, but not a password. | Failed | The password field was missing from the login screen. | FINDING_2
[5 empty] | 3. The user clicks the "log in" button |  | The user is successfully logged in and is redirected to the following screen |  | To do
TEST_5 | 1 | 5 | decision table | Unit | Unit_test Name_2 | None | PASS | PASS | Passed
TEST_6 | 1 | 3 | edge | Unit | Unit_test Name_6 | None | PASS | FAIL | Failed |  | FINDING_4

## TEST_PLAN_4
Project group: | Group 8 |  |  |  | Tests made by: | John
[5 empty] | Date: | 2024-04-23
Tests executed by:
Date:
[12 empty] | To do | Hoog
Test case ID | User Story | Acceptance Criteria | Test Design Technique | Test Type | Test Steps | Test data (if applicable) | Expected result | Actual result | Status | Notes | Finding ID | In progress | Gemiddeld
TEST_1 | 1 | 4 | syntactic | System | 1. the user clicks the "log in" button 1. the user clicks the "log in" button |  | The user will be redirected to the following screen to enter a username and password |  |  |  |  | Passed | Laag
[5 empty] | 2. The user enters a valid username and password | Username: EliseBijl Password: Test1234! | The user name and password can be entered in the appropriate fields |  |  |  |  | Failed
[5 empty] | 3. The user clicks the "log in" button |  | The user is successfully logged in and is redirected to the following screen |  |  |  |  | Reopen
TEST_2 | 1 | 5 | decision table | Unit | Unit_test Name_1 | None | PASS
TEST_3 | 1 | 3 | edge | Unit | Unit_test Name_1 | None | PASS
TEST_4 | 2 | 1 | syntactic | System | 1. the user clicks the "log in" button 1. the user clicks the "log in" button |  | The user will be redirected to the following screen to enter a username and password
[5 empty] | 2. The user enters a valid username and password | Username: EliseBijl Password: Test1234! | The user name and password can be entered in the appropriate fields
[5 empty] | 3. The user clicks the "log in" button |  | The user is successfully logged in and is redirected to the following screen
TEST_5 | 6 | 1 | decision table | Unit | Unit_test Name_1 | None | PASS
TEST_6 | 6 | 3 | edge | Unit | Unit_test Name_1 | None | PASS
TEST_7 | 7 | 7 | decision table | Unit | Unit_test Name_1 | None | PASS
TEST_8 | 3 | 1 | edge | Unit | Unit_test Name_1 | None | PASS
TEST_9 | 1 | 3 | decision table | Unit | Unit_test Name_1 | None | PASS
TEST_10 | 5 | 4 | edge | Unit | Unit_test Name_1 | None | PASS

## Sprint_4
Project group: | Project B |  |  |  | Tests made by: | Zhangyi
| Team D |  |  |  | Date: | 21 th May
[5 empty] | Tests executed by: | Zhangyi
[5 empty] | Date: | 22th May
[13 empty] | To do | Hoog
Test case ID | User Story | Acceptance Criteria | Test Design Technique | Test Type | Test Steps | Test data (if applicable) | Expected result | Actual result | Status | Notes | Finding ID |  | In progress | Gemiddeld
TEST_1 | 1 | 4 | syntactic | System | 1. the user clicks the "log in" button |  | The user will be redirected to the following screen to enter a username and password |  | Passed |  |  |  | Passed | Laag
[5 empty] | 2. The user enters a valid username and password |  | The user name and password can be entered in the appropriate fields |  | Passed |  |  |  | Failed
[5 empty] | 3.1. The User clicks the "log in" button | Username: pet Password: pet | The user is successfully logged in and is redirected to the user menu |  | Passed |  |  |  | Reopen
[5 empty] | 3.2. The Admin clicks the "log in" button | Username: Admin Password: Admin123 | The user is successfully logged in and is redirected to the admin |  | Passed
TEST_2 | 2 | 8 | syntactic | System | 1. The user clicks "Make reservation" |  | The user will be redirected to a screen with all flights then prompted for a flightnumber |  | Passed
[5 empty] | 2. The user inputs a flightnumber |  | The flight is selected and user get redirected to a screen to make seat reservations |  | Passed
[5 empty] | 3. The user input how many seats they want to reserve |  | User is redirected to screen where they have to input contactinfo for each seat |  | Passed
[5 empty] | 4. The user inputs contactinfo for each seat |  | The contactinfo gets validated if wrong format user has to input again |  | Passed
[5 empty] | 5.1. If only 1 seat was chosen, user chooses for random seat assignment |  | A random seat gets selected for the user |  | Passed
[5 empty] | 5.2. if more than 1 seat was chosen, user selects seats location on the plane |  | User selects which seats they want |  | Passed
[5 empty] | 6. User chooses seat quality |  | The user sees a menu where they can select their seat quality |  | Passed
[5 empty] | 7. User confirms the chosen seats are correct |  | An overview of the plane with the selected seats is shown |  | Passed
[5 empty] | 8. User presses any button to go back the menu |  | Reservation is made and user goes back the the main menu |  | Passed
TEST_3 | 3 | 5 | syntactic | System | 1. User clicks "Change reservation" |  | User gets redirected to a screen with all reservations |  | Passed
[5 empty] | 2. User inputs flight number |  | Flight get selected. Redirected to screen to edit flight details | prints "flightnumber does not exist" then continues the program | Passed |  | Finding_1 | prints "flightnumber does not exist" even though it does exist. Afterwards continues program as normal
[5 empty] | 3. User selects what flight detail they want to edit |  | Current flight details are shown. |  | Passed
[5 empty] | 4. User selects destination and inputs a new destination |  | User changes the destination to something else |  | Passed
[5 empty] | 5. User presses any key to go back to the main menu |  | User goes back to the main menu |  | Passed
TEST_4 | 3 | 2 | syntactic | System | 1. User clicks "Remove reservation" |  | User gets redirected to a screen with all reservations |  | Passed
[5 empty] | 2. User inputs the reservationnumber |  | Reservation is removed and user get redirected back to the main menu |  | Passed
TEST_2 | 1 | 5 | decision table | Unit | Unit_test Name_1 | None | PASS |  | Passed
TEST_3 | 1 | 3 | edge | Unit | Unit_test Name_1 | None | PASS |  | Passed

## Sprint_5
Project group: | Project B |  |  |  | Tests made by:
| Team D |  |  |  | Date:
Tests executed by:
Date:
[12 empty] | To do | Hoog
Test case ID | User Story | Acceptance Criteria | Test Design Technique | Test Type | Test Steps | Test data (if applicable) | Expected result | Actual result | Status | Notes | Finding ID | In progress | Gemiddeld
TEST_1 | 1 | 4 | syntactic | System | [7 empty] | Passed | Laag

## Detail1 (hidden)
Details for Aantal testgevallen - Status: Failed
Status
Failed